## Project Diary
Peer Evaluation system
Date | Project events | The label
2nd March 2020 | T1 2020 was start. Yao lu, Arun and Kishan formed a team to finish the project. We made a decision to choose the OpenLaw as our project. | Start
16th March 2020 | Appointment with our team's advisor Mr. Manish, who gave us some suggestions for our plans of the OpenLaw. | Advisor
17th March 2020 | Robert asked us to choose another project from the moodle list or to communicate with the owner of the OpenLaw. Because our plans of the project was not the owner of the OpenLaw's requirements, so we cannot to finish the project as the needs must come from the true requirments from the client or real needs. | Changing project
18th March 2020 | We chose the peer evaluation system as our new project to due with the issues of the situation of our project. | New start
19th March 2020 | Our group met with Gandla to discuss the proposal, and she agreed with our work and suggested many changes. | Proposal
24th March 2020 | The New Zealand government has ordered all schools to close because of the global outbreak of the coronavirus. The group members had to work from home.This had an impact on our project. | Level 3,4
13th April 2020 | Finished the first draft of the project designing pages. https://9kgazy.axshare.com | Designing
19th April 2020 | Finished the demo page of the developing for the peer evaluation. Yao Lu based on the previous project code framework, a Java web project code page was built from the front page to the background database code, and the code was deployed to the cloud server. http://peer.nzlouis.com | Developing
28th April 2020 | Complete the project division. Arun is responsible for related functions of people, including all functions of people page, design of user login, password change and other pages, database design, development and test. Arun is also responsible to write the weekly report. Kishan is responsible for related functions of home page, evaluation pages that include page designing, database design, developing and testing.Kishan is also responsible to write the meeting report. Yao Lu is responsible for other functions. | Plans